## DACF
2024 DISTRICT ASSEMBLIES COMMON FUND BUDGET
TABULAR PRESENTATION OF PROJECTS AND PROGRAMMES BY SECTOR-2024
S/N | PROJECT TITLE | LOCATION | PROJECT STATUS | BUDGET/CONTRACT SUM | PREVIOUS EXP/YET TO BE PAID GH¢ | 2024 ESTIMATE
ECONOMIC VENTURES
A. INDUSTRY
1 | Acquisition of 1no. 50KVA mounted transformer for cassava factory | Mun. Wide | On-going | 89608 | 49608 | 40000
2 | Support to BAC/Rural Technology Facility/LED | Mun. Wide | New | 20000 |  | 20000
B. ELECTRICITY
3 | Procurement of Electricity Poles and Accessories | Mun. wide | New | 100000 |  | 100000
C. MARKET
4 | Construction of 1no 11 unit Market shed with Urinal | Kyekyebiase | On-going | 88041 | 42395.4 | 45645.6
5 | Maintenance of Market | Mun. wide | New |  |  | 50000
D. AGRIC
6 | Modernisation of Agriculture | Mun. Wide | New | 40000 |  | 40000
7 | Implementation of planting for food and jobs/planting for export and Rural development | Mun. Wide | New | 30000 | ` | 30000
STREET NAMING
8 | Street Naming (Preparation of address maps and sensitisation-1,500 streets) | Mun. Wide | New | 20000 |  | 20000
ROADS
9 | Rehabilitation of Roads in the Municipality (20km) | Mun. Wide | New | 100000 |  | 100000
SOCIAL SERVICES
A. EDUCATION
10 | Construction of 1 No 3 Unit Classroom Block, Ancilliary Facilities | Ohenenkwanta | On going | 383882 | 272678.47 | 111203.53
11 | Municipal Education Fund (2%) | Mun. wide | New | 17927.6 |  | 17927.6
12 | Renovation of Existing Class room blocks (5N0.) | Mun. wide | New | 100000 |  | 100000
13 | Provision of Educational Furniture (1,000 No.) | Mun. Wide | New | 100000 |  | 100000
B. HEALTH
14 | Support Roll back Malaria (0.05%) | Mun. wide | New | 4481.9 |  | 4481.9
15 | Support to HIV/AIDS Programme (0.05%) | Mun. wide | New | 4481.9 |  | 4481.9
16 | Procurement and installation of Solar pannel at Nsiakrom CHPS Compound | Nsiakrom | New | 30000 |  | 30000
17 | Support to Public Health Education | Mun. wide | New | 30000 |  | 30000
C. COMMUNITY SELF HELP PROJECT
18 | Support to Community Self Help Projects (5%) | Mun. wide | New | 44819 |  | 44819
D. DISASTER MANAGEMENT
19 | Disaster Prevention and Management | Mun. wide | New | 50000 |  | 50000
E. GOVERNANCE STRUCTURES
20 | Support to Sub Municipal Sub Structures (2%) | Mun. wide | New | 17127.6 |  | 17127.6
21 | Public Fora/Town hall meetings | Mun. wide | New | 80000 |  | 80000
F. SECURITY
22 | Support to Security Services | Mun. Wide | New | 60000 |  | 60000
G. BOREHOLE
23 | Maintenance of 10 No. Boreholes and Water Improvement system in the municipality | Mun -Wide | New | 40000 |  | 40000
ADMINISTRATION
A. HUMAN RESOURCE MANAGEMENT
24 | Local Training Programme | Mun. wide | New | 30000 |  | 30000
B. OFFICE FACILITIES & EQUIPMENT
25 | Procurement/Maintenance of Office Machines/ Computers/Furniture | Mun wide | New | 120000 |  | 120000
26 | Printed materials and Stationary | Mun wide | New | 100000 |  | 100000
C. MPCU ACTIVITIES/PROJECT MANAGEMENT
27 | Project Management/ Monitoring of projects and support to MPCU | Mun. wide | New | 100000 |  | 100000
28 | Preparation of Annual Action Plan and Preparation of Composite Budget (Stakeholders engagement/Meetings etc) | Konongo | New | 100000 |  | 100000
DEPARTMENTS OF THE ASSEMBLY
29 | Support to Agric Dept | Konongo | New | 20000 |  | 20000
30 | Support to Comm. Devt and Social Welfare Dept | Konongo | New | 15000 |  | 15000
31 | Support to Statistical Departnment | Konongo | New | 15000 |  | 15000
32 | Support to Human Resource Dept | Konongo | New | 15000 |  | 15000
33 | Support to Urban Roads | Konongo | New | 15000 |  | 15000
34 | Support to Physical Planning Dept | Konongo | New | 15000 |  | 15000
35 | Support to Works Dept | Konongo | New | 15000 |  | 15000
36 | Support to Information Service Department | Konongo | New | 15000 |  | 15000
37 | Support to Sports and Culture | Konongo | New | 15000 |  | 15000
D. NATIONAL DAY CELEBRATION
38 | National Day Celebrations (Farmers Day, 6th March and 1st July) | Mun. wide | New | 150000 |  | 150000
CAPITAL EXPENDITURE
B. ACCOMMODATION
39 | Renovation of MCD, Asst Dir and Asst Engineer Bungalow at Low Cost | Konongo | On-going | 199258 | 79925.8 | 119332.2
40 | Renovation of Planning, Budget and Finance Officers Bungalow at Konongo-Extension | Konongo | On-going | 199943 | 19994.3 | 179948.7
41 | Renovation of Procurement Officer's Bungalow at Konongo Extension | Konongo | On-going | 168497 | 16849.7 | 151647.3
42 | Rehabilitation of the Official Residence of Mun. Director of Agriculture at Konongo Extension | Konongo | On-going | 393230 | 99323 | 293907
43 | Renovation of Assembly Residential Buildings (INFO, NIB, FIRE COMMANDER, AUDIT) | Konongo-Odumasi | New | 500000 |  | 500000
44 | Construction of Fence wall around the Municipal Assembly Office | Konongo-Odumasi | New | 250000 |  | 250000
ENVIRONMENT
A. SANITATION
45 | Waste Management (Local) | Mun. Wide | New | 100000 |  | 100000
46 | Liquid waste management | Mun. Wide | New | 30000 |  | 30000
OTHERS
| GRAND TOTAL |  |  |  |  | 3500522.33

## DACF-RFG
DACF-RFG BUDGET 2024
S/N | PROJECT TITLE | LOCATION | PROJECT STATUS | ESTIMATE | PAYMENT TO DATE | PROVISION 2024 GH¢
SOCIAL SECTOR
1 | Construction of 1no. CHPS Compound at Nsiakrom | Nsiakrom | Completed | 471699.2 | 424502 | 47197.2
2 | Capacity Building | mun wide | New | 45859 |  | 45859
3 | Drilling and mechanisation of 4 no. borehole (RETENTION) | odumasi market, konongo market, Konongo lorry station, kyekyeware | Completed | 165000 | 152716 | 12284
4 | Construction of 1no. 3unit classroom block with Ancillary Facilities | Dwease RC | Completed | 400000 | 359156.7 | 40843.3
5 | Construction of 1no. 1 storey 6unit classroom block with Ancillary Facilities | Odumasi Presby | Completed | 800000 | 719008.2 | 80991.8
6 | Construction of 1no. 3unit classroom block with Ancillary Facilities (NEW PROJECT) | KOSS MODEL A | New | 350000 |  | 350000
7 | Construction of Mechanise borehole | mun wide | New | 300000 |  | 300000
8 | Construction of 1No. CHPS compound | Agyareago | New | 500000 |  | 500000
9 | Rehabilitation of fire service and social welfare offices | Mun wide | new | 373541 |  | 373541
|  |  |  | 3406099.2 | 1655382.9 | 1750716.3

## 2024 AAP
ASANTE AKIM CENTRAL MUNICIPAL ASSEMBLY
2024 COMPOSITE ANNUAL ACTION PLAN
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
ECONOMIC
1 | Support to BAC/Rural Technology facility/LED | Municipal Wide | DACF | X | X | X |  | 20000 | BAC | Central Administration
2 | Construction of 1No. 11 unit Market shed with Urinal | Kyekyebiase | DACF | X | X | X | X | 88041 | Works | Central Administration
3 | Maintenance of Market | Municipal Wide | DACF | X | X | X | X | 50000 | Works | Central Administration
4 | Modernisation of Agriculture | Municipal Wide | DACF | X | X | X | X | 40000 | Agric | Central Administration
5 | Renovation of Odumasi Market | odumasi | DACF/RFG | X | X | X | X | 277233.2 | Works
6 | Renovation of meat house | Konongo Central market | DACF | X | X | X | X | 43000 | Works | Agric
7 | Support the implementation of MAG activities/ planting for food and jobs/planting for export and Rural development phase II | Municipal Wide | DACF | X | X | X | X | 30000 | Agric
SOCIAL DEVELOPMENT
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
8 | Construction of 1 No 3 Unit Classroom Block, Ancilliary Facilities | Ohenenkwanta | DACF | X | X |  |  | 383882 | GES | Works
9 | Provision of Educational Furniture | Municipal Wide | DACF | X | X | X | X | 100000 | GES | Works
10 | Organise outreach programme on malaria prevention and control | Municipal Wide | DACF | X | X | X | X | 4481.9 | GHS | Central Administration
11 | Implement the activities of Municipal AIDS committee | Municipal Wide | DACF | X | X | X | X | 4481.9 | GHS | Central Administration
12 | Organise public Health Education on Environmental sanitation and Hygiene. | Municipal Wide | DACF | X | X | X | X | 30000 | GHS | Central Administration
13 | Organise Local Training Programme for SMEs | Municipal Wide | DACF | X | X | X | X | 20000 | BAC | AGRIC
14 | Procurement and installation of Solar pannel at Nsiakrom CHPS Compound | Nsiakrom | DACF | X | X | X | X | 30000 | Works | Central Administration
15 | Maintenance of 10 No. Boreholes and Water Improvement system in the municipality | Municipal Wide | DACF | X | X | X | X | 40000 | Works | Central Administration
16 | Construction of 1No. CHPS compound | Agyareago | DACF/RFG | X | X | X | X | 500000 | Works | Central Administration
17 | Rehabilitation of fire service and social welfare offices | Municipal Wide | DACF/RFG | X | X | X | X | 373541
18 | Construction of 1 No. 3 Unit classroom block with office, store and staff common room | Dwease | DACF/RFG | X | X | X | X | 40843.3 | Works | Central Administration
19 | Construction of 1 No. 1storey 6 Unit classroom block with office, store and staff common room | Odumasi Presby | DACF/RFG | X | X | X | X | 80991.8 | Works | Central Administration
20 | Construction of 1No. 3-Unit Classroom Block with Ancillary Facilities at KOSS Model School | KOSS Model School | DACF/RFG | X | X | X | X | 350000 | Works | Central Administration
21 | Renovation of MCD, Asst Dir and Asst Eng Bungalow | Konongo Lowcost | DACF | X | X | X | X | 199258 | Works | Central Administration
22 | Reroofing of OU and MA 2 RC Basic school and rehabilitation of Assembly works yard | OU and MA 2 RC Basic school | DACF | X | X | X | X | 192080 | Works | GES
23 | Renovation of Planning, Budget and Finance Officer’s Bungalow | Konongo Extension | DACF | X | X | X | X | 199943 | Works | Central Administration
24 | Renovation of Procurement Officer’s Bungalow | Konongo Extension | DACF | X | X | X | X | 168497 | Works | Central Administration
25 | Rehabilitation of the Official Residence of Mun. Director of Agriculture | Konongo Extension | DACF | X | X | X | X | 393230 | Works | Central Administration
26 | Construction of footbridge | Konongo Mines Cluster of schools | DACF | X | X | X | X | 50000 | Road | Central Administration
27 | Construction of Fence wall around the Municipal Assembly Office | Konongo Extension | DACF | X | X | X | X | 250000 | Works | Central Administration
ENVIRONMENT INFRASTRUCTURE AND HUMAN SETTLEMENTS
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
28 | Procurement of Electricity Poles and Accessories | Municipal wide | DACF | X | X | X | X | 100000 | Works | Central Administration
29 | Rehabiliation of Roads (20km) | Municipal wide | Road Fund | X | X | X | X | 100000 | Road | Central Administration
30 | Organise quaterly Anti-fire campaigns | Municipal wide | DACF | X | X | X | x | 50000 | NADMO | Central Administration
31 | Undertake quarterly monitoring of small scale mining sites to ensure compliance with mining regulations | Municipal wide | DACF | x | x | x | x | 5404 | NADMO | Central Administration
32 | Conduct monthly Hazard mapping of the Municipality | Municipal wide | DACF | x | x | x |  | 5000 | NADMO | Central Administration
33 | Evacuation and levelling of refuse dumps | Municipal Wide | DACF | X | X | X | X | 100000 | MEHO | Central Administration
34 | Fumigation exercise to disinfect sanitary sites. | Municipal Wide | DACF | X | X | X | X | 307191 | MEHO | Central Administration
35 | Underatake clean up exercises and desilting of choked gutters at Central Business District and surrounding communities | Municipal Wide | DACF | X | X | X | X | 230000 | MEHO | Central Administration
36 | Organise Community Mobilizatiuon and Education Programme on child labor, unpaid care work | Atunsu, Konongo | DACF | X | X | X | X | 5400 | Social Welfare
37 | Tree Planting Exercise | Wesley High SHS | DACF | X | X | X | X | 10000 | Central Administration
38 | Community mobilization and education on parental care and coping strategies for life crisis | Patriensa, Konongo-Odumase SHS | DACF | X | X | X | X | 5000 | Social Welfare
39 | Gender based violence on cyberbullying | KOSS Model A School | DACF | X | X | X | X | 7000 | Social Welfare
40 | Public Education on Noise pollution and Air Quality Control | Municipal Wide | DACF | X | X | X | X | 5000 | MEHO | Central Administration
41 | Dislodge and dispose liquid waste to final disposal site at Bomireso | Municipal Wide | DACF | X | X | X | X | 30000 | MEHO | Central Administration
GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY
No | Activity | Location | Source of Funds | Time Schedule |  |  |  | Budget (GH¢) | Implementing Agency
|  |  |  | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr |  | Lead | Collaborating
42 | Public Education on Revenue Mobilization | Municipal Wide | DACF | X | X | X | X | 8000 | Finance | Central Administration
43 | Redevelopment of Jubilee park | Konongo-odumasi | IGF | X | X | X | X | 248205 | Works | Central Administration
44 | Street Naming | Municipal Wide | DACF | X | X | X | X | 20000 | PPD | Central Administration
45 | Fabrication of 56 no. metal gratings (drainage covers) on open drains | Konongo main station | DACF | X | X | X | X | 22000 | Works | Central Administration
46 | Support to Sub Municipal Structures (2%) | Municipal Wide | DACF | X | X | X | X | 17127.6 | Central Administration
47 | Organise Public fora/town hall meetings on Government policies and interventions | Municipal Wide | DACF | X | X | X | X | 80000 | Central Administration
48 | Support to Community Self Help Projects (5%) | Municipal Wide | DACF | X | X | X | X | 44819 | Central Administration
49 | Municipal Education Fund (2%) | Municipal Wide | DACF | X | X | X | X | 17927.6
50 | Organise quarterly and emergency Municpal Security Committee meetings (MUSEC) | Municipal Wide | DACF | X | X | X | X | 60000 | Central Administration
51 | Procurement/Maintenance of Office Machines/Computers/Furniture | Municipal Wide | DACF | X | X | X | X | 120000 | Central Administration
52 | Procurement of stationaries | Municipal Wide | DACF | X | X | X | X | 100000 | Central Administration
53 | Maintenance and repairs of Official vehicles | Municipal Wide | DACF | X | X | X | X | 45000 | Central Administration
54 | Project Management/Monitoring of projects and support to MPCU | Municipal Wide | DACF | X | X | X | X | 100000 | Central Administration
55 | Construction and completion of marriage registry | Konongo-odumasi | IGF | X | X | X | X | 200000 | Works | Central Administration
56 | Preparation of Medium Term dev't Plan and Preparation of Composite Budget (Stakeholders engagement/Meetings etc) | Konongo | DACF | X | X | X | X | 100000 | Central Administration
57 | Support to Departments | Konongo | DACF | X | X | X | X | 140000 | Central Administration
58 | Operation and Maintenance (Assembly Office and Buildings) | Konongo-Odumasi | DACF | X | X | X | X | 77169.85 | Works | Central Administration
59 | National Day Celebrations (Farmers Day, 6th March and 1st July) | Municipal Wide | DACF | X |  |  | X | 150000 | Central Administration
60 | Organise capacity building programmes for staff of the Assembly | Municipal Wide | DACF-RFG | X | X | X | X | 45859 | HR | Central Administration
61 | Sensitization Of Pupils Of On Zebra Crossing (Kumasi-Accra Highway) | Pinamang school | DACF | X | X | X | X | 20000 | Central Administration

## Sheet2
| Construction of 1No. CHPS compound | Agyareago | DACF/RFG | X | X | X | X | 500000 | Works | Central Administration
10 | Procurement and installation of Solar pannel at Nsiakrom CHPS Compound | Nsiakrom | DACF | X | X | X | X | 30000 | Works | Central Administration
13 | Construction of 1No. 3-Unit Classroom Block with Ancillary Facilities at KOSS Model School | KOSS Model School | DACF/RFG | X | X | X | X | 350000 | Works | Central Administration
| Renovation of Assembly Residential Buildings (INFO, NIB, FIRE COMMANDER, AUDIT) | Konongo Extension | DACF | X | X | X | X | 500000 | Works | Central Administration
| Construction of Fence wall around the Municipal Assembly Office | Konongo Extension | DACF | X | X | X | X | 250000 | Works | Central Administration
Landscaping of Assembly environment